HERE!

Face Recognition Attendance System

Production Readiness Roadmap & Cost Analysis

Prepared by:  SRM KTR B.Tech CSE — 4th Semester

For Departmental Review & Implementation Planning

March 2026

# 1. Executive Summary

HERE! is a functional, locally-deployed face recognition attendance system built on Flask, Facenet512, and Next.js. The core recognition engine works well. What it currently lacks is everything needed to run reliably in a production college environment: cloud hosting, authentication, real integrations with Zoho, mobile apps for teachers and students, and the appeal/notification workflow you want.

This document maps out exactly what needs to be built, how long it will take, what it will cost per month in INR, and what risks to plan for.

# 2. What the System Does Today (Current State)

The following features are built and working:

- Face registration: manual (5–8 photos) and bulk via Excel

- Self-registration via secure token links

- Attendance via classroom photo(s) — single and batch

- Live webcam attendance mode

- Add more face embeddings to improve recognition per student

- Manual attendance override from dashboard

- Unrecognized face crop saving for review

- SQLite database with WAL mode and indexed queries

The system runs on localhost only, with no authentication, no mobile app, no notifications, and no Zoho integration. It is a solid proof-of-concept, not yet production-ready.

# 3. What Still Needs to Be Built

The table below covers all the work required, prioritized by urgency. P0 = must-have before going live, P1 = needed for the full workflow you described, P2 = important but can be done after launch.

| Module | What Needs to be Built / Changed | Effort | Priority |
| --- | --- | --- | --- |
| Zoho Integration | Connect POST /attendance/mark to Zoho People API. OAuth2 token management, field mapping (roll no → Zoho employee ID), retry on failure. | 2–3 wks | P0 |
| Authentication & Roles | JWT/session login for teachers. Admin (HOD/principal), teacher, and student roles. Currently zero auth — critical security gap. | 1–2 wks | P0 |
| Multi-Section Support | Sections A1–S2 database schema. Teacher assigned to section(s). Attendance scoped per section+date. Filter views. | 1 wk | P0 |
| Absence Notification | After attendance is processed, send SMS/push to absent students. MSG91 or Firebase. Include student name + date + course. | 1 wk | P1 |
| Student Appeal Flow | Student receives notification → taps 'Appeal' → app captures device GPS → sends to teacher's dashboard. Teacher approves/rejects → auto-updates Zoho. | 2–3 wks | P1 |
| Mobile App (Teacher) | React Native app: take 4–5 classroom photos, select section, submit. View results. Approve appeals. Replaces the Next.js browser UI for daily use. | 3–4 wks | P1 |
| Mobile App (Student) | React Native app: receive push notifications, appeal with location, view own attendance %. | 2–3 wks | P1 |
| Cloud Deployment | Dockerize Flask backend. Deploy to AWS/GCP. HTTPS, nginx reverse proxy, auto-restart on crash. | 1–2 wks | P0 |
| SQLite → PostgreSQL | Swap ORM layer (already isolated in database.py). Required for multi-teacher concurrent access. | 3–5 days | P0 |
| Bulk Registration Revamp | Drive-based registration is fragile (quota limits). Build proper upload portal with progress bar and validation. | 1 wk | P2 |
| Attendance Export | Export to Excel per section/date range. Historical heatmap. Currently missing from the frontend. | 3–5 days | P2 |
| Admin Dashboard | SRM admin view: all sections, per-teacher stats, system health, student counts, accuracy reports. | 1–2 wks | P2 |

# 4. Zoho People Integration — Deep Dive

This is the most critical integration. Here is how it works technically:

How Zoho People Attendance API Works

- Zoho People has a REST API under the 'Attendance' module.

- You authenticate via OAuth2 — your app gets a client ID and secret from Zoho Developer Console.

- You call POST /attendance/bulkupdate with an array of employee IDs, date, check-in/check-out times.

- Employee IDs in Zoho must be mapped to student roll numbers in your database (one-time setup per student).

- SRM may already have a Zoho People organizational account — check with the IT department; this saves you needing to create one.

What You Need to Build

- An OAuth2 token manager in the backend (store access + refresh tokens, auto-renew)

- A mapping table: roll_no ↔ zoho_employee_id in your database

- After each attendance session: POST the present/absent list to Zoho asynchronously (don't block the main result)

- A retry queue for failed Zoho calls (network timeouts, API rate limits)

- A reconciliation job: once a day, verify Zoho records match your DB

Zoho People Plan Required

You need at least Zoho People Standard Plan (approx ₹100–120 per user/month) for API access to the Attendance module. Talk to your college administration — if SRM already pays for Zoho, you just need API credentials from the IT team.

# 5. The Appeal Flow — How It Should Work

This is the most user-visible feature. Here is the full flow:

Step-by-Step

- Step 1 — Attendance processed: Teacher takes 4–5 photos, system marks attendance within ~10–15 seconds.

- Step 2 — Notification sent: All absent students get a push notification (or SMS) within 1 minute saying they were marked absent for [Course] on [Date].

- Step 3 — Appeal window: Student has 10 minutes to tap 'I was present — appeal'. The app captures their GPS location at that moment.

- Step 4 — Teacher sees appeal: A notification appears on the teacher's app showing: student name, roll no, GPS location, timestamp of appeal, and a map pin.

- Step 5 — Teacher approves or rejects: One tap. If approved, the backend marks present in your DB and calls the Zoho API to update.

- Step 6 — Student notified: Student gets confirmation their appeal was accepted/rejected.

Technical Requirements for Appeal Flow

- A new appeals table in the database: student_id, session_id, gps_lat, gps_lon, appeal_timestamp, status, reviewed_at

- Push notifications using Firebase Cloud Messaging (FCM) — free and reliable

- Student mobile app with GPS permission

- Teacher mobile app with push inbox + approve/reject UI

- 10-minute server-side expiry enforced on all appeal submissions

- Location sanity check: flag if GPS is far from the classroom building (optional anti-fraud measure)

# 6. Development Timeline

Estimated timeline assuming you work on this with 1–2 other developers, or part-time on your own. Solo: add 30–40% to all estimates.

| Phase | Duration | Deliverables |
| --- | --- | --- |
| Phase 1 | Weeks 1–2 | Production server setup, HTTPS, SQLite → PostgreSQL, JWT auth + teacher login, multi-section schema |
| Phase 2 | Weeks 3–5 | Zoho People API integration, absence SMS notifications (MSG91), attendance export to Excel |
| Phase 3 | Weeks 6–9 | Teacher mobile app (React Native), student mobile app, appeal flow with GPS |
| Phase 4 | Weeks 10–11 | Admin dashboard, bulk registration portal revamp, audit logs |
| Phase 5 | Weeks 12–14 | Pilot with 2–3 sections, stress testing, accuracy tuning, feedback loop |
| Phase 6 | Week 15+ | Full college rollout, teacher training, documentation, ongoing monitoring |

# 7. Cost Breakdown (INR)

## 7.1 Monthly Infrastructure & Service Costs

| Component | Details | Monthly Cost (INR) |
| --- | --- | --- |
| Cloud Server (AWS/GCP/Azure) | 4 vCPU, 16 GB RAM, 100 GB SSD — needed for ML inference | ₹3,500 – ₹5,000 |
| GPU Instance (optional but recommended) | T4 GPU on GCP — 5x faster face recognition | ₹6,000 – ₹10,000 |
| Database (PostgreSQL) | Managed DB (RDS/Cloud SQL) or self-hosted upgrade from SQLite | ₹1,500 – ₹2,500 |
| Storage (S3/GCS) | Photo storage for registration images + unrecognized crops | ₹200 – ₹500 |
| Zoho People API | Zoho People Standard Plan (per user) — attendance write access | ₹100–₹120/user/mo |
| SMS / Push Notifications | MSG91 or Twilio (SMS for absent alerts) — per message billing | ₹0.15–₹0.30 per SMS |
| FCM Push (Firebase) | Google Firebase Cloud Messaging — free tier | ₹0 (free) |
| Domain + SSL | Custom domain (e.g., here.srmktr.edu.in) + Let's Encrypt | ₹800 – ₹1,200/year |
| Mobile App (Android/iOS) | React Native — one codebase for both platforms | One-time dev cost |
| ESTIMATED MONTHLY TOTAL | (Without GPU / small pilot) | ₹6,000 – ₹10,000 / mo |
| ESTIMATED MONTHLY TOTAL | (With GPU / full college deployment) | ₹12,000 – ₹20,000 / mo |

## 7.2 One-Time / Setup Costs

These are costs you pay once, not monthly:

| Item | Estimated Cost (INR) |
| --- | --- |
| Mobile App Development (if hiring freelancers) | ₹50,000 – ₹1,20,000 |
| College server hardware (alternative to cloud) | ₹30,000 – ₹60,000 (one-time) |
| Domain name registration (3 years) | ₹2,000 – ₹4,000 |
| Zoho People setup + SRM IT consultation | ₹0 if IT dept handles, else ₹5,000 |
| Student data consent form printing / distribution | ₹2,000 – ₹5,000 |

## 7.3 Practical Cost-Saving Options for a College Project

- Apply for Google for Startups or AWS Activate — both give $5,000–$10,000 in free cloud credits for student projects. This can fund 6–12 months of hosting.

- Apply through SRM's incubation cell or the startup cell — they sometimes sponsor hosting costs for promising student projects.

- Start with no GPU — CPU inference is slower but works fine for a pilot with 1–2 sections. Only upgrade to GPU after validating the system.

- Self-host on a college server if the IT department is willing — eliminates monthly cloud costs entirely for a pilot.

- Firebase is free for the notification tier you need — no cost there.

# 8. Architecture Changes for Production

The current architecture is fine for localhost but needs these changes before deploying to the college:

Backend Changes

- SQLite → PostgreSQL: Your database.py is already cleanly separated. This is a 3–5 day migration and critical for multiple teachers using the system simultaneously.

- Add JWT authentication middleware to all admin routes. Currently any request to /register_face, /process_attendance, etc. is unauthenticated.

- Dockerize the Flask app so it can be deployed to any cloud or server reliably.

- Add rate limiting to prevent accidental or intentional DDoS from the mobile apps.

- Add a background job queue (Celery + Redis, or just APScheduler) for async Zoho sync and notification sending.

Frontend Changes

- The Next.js web app becomes the admin/HOD panel — not the primary teacher interface.

- The primary teacher interface becomes the mobile app (React Native).

- Add proper login page and session management.

- Add an attendance history export (Excel) page — this is already listed as a gap.

New Components

- React Native mobile app (teacher): photo capture, section select, results view, appeal inbox

- React Native mobile app (student): push notification receiver, appeal submit with GPS, attendance history

- Nginx reverse proxy in front of Flask for SSL termination and load handling

- FCM integration for push notifications

- Zoho OAuth2 token management module

# 9. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Zoho API schema changes or rate limits | High | Cache daily attendance batch; write async queue; have fallback CSV export ready |
| Poor classroom lighting → low accuracy | High | Add CLAHE as default (not just for blurry images). Require teachers to use flash or ensure lights are on |
| Students wearing masks/hats → missed recognition | Medium | Train with masked photos during registration; manual override is already built |
| GPU instance cost overrun | Medium | Start without GPU (CPU only); only add GPU if >30 students/class and speed is unacceptable |
| Google Drive quota hitting rate limit on bulk import | Medium | Build dedicated photo upload portal as alternative to Drive links |
| Student location spoofing in appeals | Medium | Cross-check appeal timestamp with attendance timestamp; flag appeals >10 min late |
| No college IT support / hosting | High | Self-host on a server in the college network (a ₹30,000 one-time server is an option) |
| PDPA / data privacy compliance | Medium | Store embeddings not raw photos; publish clear data retention policy; get student consent forms |

# 10. Things You Didn't Ask About — But Must Address

Your sir asked for a comprehensive picture. These are issues that will come up whether you plan for them or not:

Data Privacy & Legal (VERY important)

- Biometric data (face embeddings) is sensitive personal data under India's Digital Personal Data Protection Act 2023 (DPDPA). You need explicit written consent from every student before storing their data.

- You should have a data retention policy: how long are embeddings stored? What happens when a student leaves?

- Currently raw photos are stored in /uploads/ temporarily. In production, delete these immediately after embedding generation. Never store raw face photos longer than needed.

- Display a privacy policy on the self-registration page — this is not optional for a real institution.

Accuracy Monitoring

- Track false positive and false negative rates per section over time. Your current system has no analytics on its own accuracy.

- Build a feedback loop: if a teacher frequently overrides the system's result for a specific student, flag that student for re-registration with better photos.

- The 0.769 threshold may need tuning per section (e.g., a section that meets in a dimly lit lab vs. a bright lecture hall).

Scalability: How Many Students?

- SRM KTR has roughly 15,000+ students. If this scales beyond one department, the Facenet512 cosine similarity matrix grows: 15,000 students × 512 dimensions = ~30 MB in RAM, which is still fast. But you should benchmark at 1,000+ students before claiming it scales.

- The real bottleneck will be concurrent teacher sessions: 50 teachers all uploading photos at the same time. Load test before college-wide rollout.

Internet Connectivity in Classrooms

- SRM KTR has Wi-Fi but classroom connectivity can be inconsistent. The mobile app should support offline queueing: take photos, recognize locally if possible, then sync to server when online.

- Offline recognition is hard (ML model on device), but offline photo queueing + cloud sync is straightforward.

Handling New Students Mid-Semester

- Late admissions or section changes need a re-registration flow. Make sure the admin can easily reassign a student to a different section without breaking attendance history.

Accessibility for Teachers

- Teachers at SRM range from very tech-savvy to not at all. The app needs to be dead simple: open app, select class, take photos, done. No more than 3 taps to submit attendance.

- Provide a 1-page illustrated quick-start guide. Resistance from faculty is the single biggest killer of adoption.

Fallback When System Fails

- What happens if the server is down during a class? Teachers need a fallback: either a cached local mode or a manual entry fallback that syncs to Zoho later.

- The current system has no offline mode at all — this is a gap.

# 11. Recommended Approach for Your Sir

Given that this is a student project being evaluated for real-world implementation, here is the practical recommendation:

Phase 1: Pilot (Recommended Starting Point)

- Deploy to a single college server or a cheap cloud VM (₹3,500/month).

- Add authentication, PostgreSQL, and section support.

- Test with 2–3 sections (one per department) for one full month.

- Measure: accuracy rate, teacher satisfaction, time saved per class.

- This phase: ~6–8 weeks of development, ~₹5,000/month running cost.

Phase 2: Add the Features Your Sir Wants

- Zoho integration, absence notifications, appeal flow, mobile apps.

- This is the full product. Takes 3–4 months total from today.

- Running cost rises to ₹8,000–₹15,000/month depending on scale.

Phase 3: Full Rollout

- Roll out to all sections A1–S2 after Phase 2 pilot proves stable.

- At this scale, negotiate with college IT for dedicated server (better value than cloud at >300 concurrent users).

The honest answer for your sir: the core ML engine is production-quality. The surrounding infrastructure (auth, deployment, integrations, mobile) is what takes 3–4 more months. Budget ₹8,000–₹15,000/month for a full deployment, or ₹0–₹5,000/month if you get Google/AWS student credits.

# 12. At a Glance — Summary

| Question | Answer |
| --- | --- |
| Is the core tech production-quality? | Yes — Facenet512 + RetinaFace is used in real products worldwide |
| How much work is left? | ~3–4 months for full feature set with Zoho + mobile apps |
| Minimum monthly cost (pilot)? | ₹5,000 – ₹8,000/month (no GPU, small cloud VM) |
| Full deployment monthly cost? | ₹12,000 – ₹20,000/month (GPU + notifications + Zoho) |
| Biggest technical gap? | No authentication, SQLite not suitable for multi-user |
| Biggest integration challenge? | Zoho People OAuth2 + employee ID mapping |
| Can you get free hosting? | Yes — Google for Startups / AWS Activate give $5,000–10,000 credits |
| What can kill the project? | Faculty resistance, poor classroom lighting, no IT dept support |
| Is this deployable at SRM scale? | Yes, with PostgreSQL + proper cloud infra — matrix search is O(1) |